Contract Agreement

for

DESIGN, PROCURE AND CONSTRUCTION OF NEW CANTEEN FACILITY

AT APM TERMINALS PIPAVAV

between

Gujarat Pipavav Port Limited

and

[Contractor]

Contract Agreement

DESIGN, PROCURE AND CONSTRUCTION OF NEW CANTEEN FACILITY AT APM TERMINALS PIPAVAV

THIS CONTRACT AGREEMENT (“Agreement”) has been made on this the …………………… at Port Pipavav, Rajula

BY AND BETWEEN

M/s Gujarat Pipavav Port Limited (GPPL) (CIN L63010GJ1992PLC018106) a company incorporated under The Companies Act, 1956 having registered office at Port of Pipavav, Post Rampara-2, via Rajula District Amreli, Gujarat 365 560 - India and Corporate Office at 301, Trade Centre, Bandra Kurla Complex, Bandra East, Mumbai and registered under number 04-18106 at the Chamber of Commerce (hereinafter called as “The Employer”) on the ONE PART,

AND

M/s ………………, a company incorporated under the laws of The Companies Act, 1956 and having its registered office at………………………………………….. (hereinafter called as “the Contractor”), which expression shall unless repugnant to the context or meaning thereof, include its administrators, successors and permitted assigns) on the OTHER PART,

The Employer and The Contractor hereinafter Individually referred to as "Party" and collectively as "Parties",

WHEREAS the Employer has awarded the works “Design, Procure and Construction of New Canteen Facility at APM Terminals Pipavav” (hereinafter referred “The Works”) to The Contractor and The Employer has accepted the final offer submitted by The Contractor.

WHEREAS the Contractor has represented and warranted that it has the relevant and adequate experience, expertise, knowledge, capability and resources to undertake execution, completion and guarantee of works on mutually convenient terms and conditions agreed as follows.

NOW THEREFORE, in consideration of the premises and mutual terms and conditions hereinafter set forth the Parties agree as follows.

The Employer and the Contractor agree as follows:

- In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to.

- The Contractor shall undertake execution and complete the work including the remedying of any defects therein, the works in respect of the scope of work detailed under annexures to this contract and the other documents/annexures shall be deemed to form and be read and constructed forming essential part of this Agreement.

- The following Annexures/Documents hereto and shall form integral part of this Agreement and for the purpose of interpretation were in event of conflict or inconsistency, the priority of documents from high to low shall be in accordance with following sequence.

  - General Conditions for this contract

  - Technical Specifications for this Contract

  - Tender Bill of Quantity for this Contract

  - Location Plan & Construction Drawings for this Contract

  - The following documents shall be essential part of this Agreement

    - APMT Guidelines on Anti-Corruption, Competition & Sanction Law and Regulations

    - APMT Guidelines on Civil Construction Safety

    - APMT Guidelines on Contractor safety

    - APMT Guidelines on Project HSE Specifications

    - APMT Guidelines on Third Party Code of Conducts

    - APMT Guidelines on Consequences Management

    - APMT Guidelines on Contract Labour Compliance

  - All Communication details during Tendring process for this contract.

- The documents/Annexure(s)/Correspondence forming part of this agreement are mutually explanatory of one other. In case of ambiguities / discrepancies the same shall be explained and adjusted by the Employer and the Engineer who shall thereon issue instructions to the Contractor in this regard. The Contractor shall accept the instructions of Employer and the Engineer without any protest or demur.

- The Contractors hereby warrants and represents that it shall execute and complete the works and remedy any defects therein in conformity with the provisions of the Contract in consideration of the payments to be made by the Employer to the Contractor as mentioned in the Agreement.

- The Employer hereby warrants and represents to pay the Contractor, in consideration of the actual execution and completion of the Works and the remedying of any defects therein, the Agreement price at the times and in the manner prescribed by the Agreement.

- Before the commencement of work, the Contractor shall prepare & submit the Work Programme Schedule (WPS) and Quality Control Plan (QCP) to the Employer for approval. The WPS and QCP shall be strictly implemented and the cost of monitoring the quality and tests etc shall be fully borne by the contractor and shall deemed to be included in Accepted Contract Amount

- Contract Price: The Accepted Contract Amount agreed by the Parties for the execution and completion of the Works and carrying out other obligations in accordance with the terms of the Contract is INR………(Rupees…………….. Only). The Parties agree that this Contract is a re-measurable Contract and shall be adjusted in accordance with the Contract.

- The Accepted Contract Amount shall be excluding Goods Service Tax (GST) payable at applicable rates, but including of all taxes, duties, levies, Labour & bocw cess, TCS, Import duty, material Royalties, transportation, inspection & certification charges, OR any other state OR corporation tax OR applicable under any rules / regulations / acts / statutes of the State and Central Government duties.

- The Accepted Contract Amount shall also include expenditure for traffic maintenance to avoid constraints of work, safety, diversion and any precautions required to execute the works and expenditure for liaising/dispute resolve with local authorities/villages.

- Employer shall deduct Gujarat State Turnover Tax on Works Contract Tax, Income Tax and any other taxes as per norms of Government of Gujarat & Government of India if applicable.

- In consideration of the payments to be made by the Employer to the Contractor as agreed between the Parties, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy the defects therein with the provisions of the Contract.

- The Employer hereby covenants to pay the Contractor in consideration of the execution, and completion of the Works and the remedying of defects therein, the Contract Price at the times and in the manner prescribed by the Contract.

- Since this is an operational port, the Contractor need to take all necessary safety measures, precautions as deemed to progress with minimal interruption. In any case, Operation will always have priority and contractor needs to plan their activities accordingly.

- Completion Period

Time is the essence of Contract. The Contractor has agreed for timely completion of work and shall deploy sufficient experienced manpower, equipment and machineries to carry out and complete the work as required by the Employer.

The time of completion of this work is 180 (one hundred eighty) Days from the date of handing over of work site.

- The Contractor has verified the site, local working environment and fully conversant with local challenges like compliance of local laws, swift synchronization with local communities, dealing with local administrations etc. The Contractor shall be singularly responsible for execution of all works inside and outside the port boundary by coordinating with the local community and authorities as required for successful completion of the Works.

- All the construction materials, plants, equipment, tools & tackles, manpower, laboratory for test and others such item required/related to this Work for satisfactory completion of the Works shall be provided by the Contractor. The Contractor shall be responsible for supply of any items, materials, equipment etc in whatever form. Final quoted price by the Contractor shall be deemed to include all the costs required for the satisfactory completion of the contract.

- Contractors shall take all necessary precautions towards safety of human beings, environments, materials, machineries, equipment & assets of GPPL and provide all safety gear including personnel protective equipment (PPE) to his workers, Engineers, staff etc as necessary considering the nature of work, at his cost.

- Project in Charge

The Employer shall nominate ……………………… as Project in Charge of this work. The Contractor shall carry out works on day-to-day basis with prior consultation of Project in Charge.

- Performance Bank Guarantee

The Contractor shall provide unconditional security for his proper performance of the Contract to the Employer within 14 (fourteen) days from the date of acceptance of contract. The Performance Security shall be in the form of a bank guarantee of nationalized bank as stipulated by the Employer and equal to 10% (ten Percent) of the Contract Award Price.

Performance Security (bank guarantee) shall be issued by a Nationalized / Scheduled Bank approved by the Employer. The cost of complying with the requirements of this clause shall be borne by the Contractor. The performance security shall be kept valid until a date, 28 days from the date of expiry of contract issued by Employer. Employer reserved the rights to claim or encash the performance security amount if the Contractor unable to perform the work as per condition of contract or contractor failed to renew the PBG (if expired) before completion of work.

- Payment condition

Contractor shall furnish his invoice/bills to the Engineer-In-Charge in a format approved by the Engineer on completion of each month for release of payment for the actual executed quantities as per Condition of Contract. Each bill amount to be 10% or more of the overall contract amount.

The Engineer-In-Charge will check and verify the invoice/bill and certify it for an amount payable after deducting the amounts as required to be deducted towards Retention Money, Income Tax, Works Contract Tax or any other tax, duty, levy that may be deductible at source or amount to be withhold/disallowed for defective works needing rectification in accordance with condition of contract and forward the invoice/bills to competent authority of the employer for payment.

The Employer shall make payment based on actual measurement of work completed by the Contractor. The Employer shall certify the mutually agreeable quantity(ies) for such item(s) measured with respect to Contractor’s notifications to The Employer issued suitably from time to time for delay occurred due to the reasons not attributable to the contractor. The Employer shall not pay for supply of excess unused quantities by the Supplier/Contractor.

The Employer shall deduct Gujarat State Turnover Tax, Works Contract Tax, Income Tax and any other taxes as per norms of Government of Gujarat & Central Government of India.

The payment shall be made within a period of 28 (twenty-Eight) days from the date of submission of technically correct application of interim payment certificate/bill. “Technically correct” means the checked, mutually agreed and signed off invoice by Employer and Contractor with all supporting and backup documents.

- Retention money

The employer shall retain 10 % (Ten percent) of the amount due in each bill.

50% of this Retention Money shall be released to the Tenderer against an invoice, within fifteen days from the date of issue of taking over certificate.

Balance 50% of the retention money shall be released to the Contractor, by the employer, on satisfactory completion of the Defect Notification/Liability Period. The Employer shall be entitled to recover any amount from the said Retention Money on account of any recoveries occurs during Defect Notification Period from the Tenderer.

- Liquidated Damages

The Time of Completion / Completion Period is essence for the contract. In case of any delay in completion of the work, the Employer shall withhold/recover liquidated damages @ 0.25% (point twenty five percent) of Contract Award Price per day, subject to a maximum of 10% (Ten percent) of the Contract Award Price plus taxes. As per the Goods & Service Tax (GST) Act, the Contractor is liable to pay GST as prevailing rate as applicable for entire work done (of contract price) amount which may include the works executed during delayed period of the contract and accordingly. The contractor shall raise E-invoice to the employer for entire work value with GST for receipt of payment from employer.

In the event, the delay is occurred due to contractors’ fault and accepted by Contractor then the Employer shall issue Debit Note for the recovery of delay damage on the contract price along with the applicable GST.

Liquidated Damage (LD) or Delay penalty shall not be applicable for the time wherein the work is being stopped by the employer for operational activities.

However, the LD penalty will be applicable for the delay in work attributed from poor planning, inadequate resource, and other various factors resulting in delay of work by the contractor. The Contractor shall not raise any disputes, controversies or questions with regard to right of the employer to impose the liquidated damages and decision taken by the employer shall be final and binding upon the contractor.

- Variation & Escalation

Variation: Employer shall reserve the right to add/alter/delete/modify any of the items or quantities of items as stipulated in the Bill of Quantities in accordance with Condition of Contract.

In the event of additional/modified items, the rates to be paid for shall be derived from the rates available for similar items in the accepted Bill of Quantities or decided based on rate analysis and as mutually agreed. In the event of dispute of any kind on the rates & scope work, The Employer will right issue the variation work to third party and shall bound the Contractor.

Escalation: No (No) Escalation shall be payable on the Works under this contract due to any reason whatsoever to the Contractor.

- Anti-Corruption Policy

  - Without prejudice to the generality of the foregoing provisions, each Party or the parties to a work order undertakes and warrants to the other party that neither it nor any member of its Affiliates, nor any agent, consultant or other intermediary acting on behalf of it or its Affiliates, shall, directly or indirectly, in relation to this Agreement or any Work Order created pursuant to it, give, promise or attempt to give, or approve or authorize the giving of, anything of value.

    - Any employee, officer or director of or any person representing the other party or the other party to a work order or its Affiliates;

    - Any other person, including without limitation any Public Official;

    - A political party or a labour union controlled by any Government or political party ; or

    - A charitable or other organization, or an officer, director or employee thereof, or any person acting directly or indirectly on behalf of the same.

for the purpose of (1) securing any improper advantage for Contractor and its Affiliates or employer; (2) inducing or influencing that Public Official improperly to take any action or refrain from taking any action in order for either Party or a party to a Work Order to obtain or retain business, or to secure the direction of business to either, or (3) inducing or influencing that Public Official to use his/her influence with any Government or public international organization, or any or any department, agency or other instrumentality thereof, for any such purpose

  - Each Party or a party to a Work Order further warrants and undertakes to the other party that

    - to the best of its knowledge, neither it nor any of its Affiliates, officers, directors, shareholders, employees, or agents or other intermediaries, or any other person acting directly or indirectly on its behalf, has carried out any of the actions described in Clause 25.2 above; and

    - The persons described in (a), above, shall comply with the provisions of this clause 25.

  - Notwithstanding the foregoing provisions, as regards small value payments to a low level Public Official for the facilitation or expedition of routine tasks which that person must perform as part of his/her job, Contractor warrants and undertakes that it and its Affiliates, officers, directors, shareholders, employees, agents or other intermediaries or any other person acting directly or indirectly on its behalf, shall fully comply with the anti-corruption policy involving such payments, including without limitation cooperating with employer to eliminate such payments.

  - Contractor warrants and undertakes that all remuneration received from employer under this Work order / Agreement or under a Purchase Order created pursuant to this Agreement is solely intended to compensate Contractor for the Work expressly provided under this Agreement, including without limitation Contractor’s related documented costs and expenses. Contractor warrants and undertakes that it is not receiving remuneration for any other purpose.

  - Contractor warrants and undertakes it shall maintain adequate records in order to be able to verify its compliance with the provisions of this Clause 19, and the other Party or the parties to a Work Order, a certified public accountant designated by the other Party/party shall be permitted to conduct an audit of such records, at the other Party’s/party’s reasonable discretion, in case of any bona-fide dispute between the Parties/parties regarding such compliance, or in case of any investigation by or allegation from any applicable public authority regarding potential violations of any relevant laws involving these matters. The Parties/parties shall cooperate in any such audit and otherwise in providing documentation relating to any such dispute or investigation.

  - Contractor warrants that all responses and related information it has given to employer’s regulatory-compliance questions prior to execution of this Agreement and undertakes that answers to all such subsequent questions shall be, accurate and complete.

  - Each party shall save, indemnify, defend and hold harmless the other party and its Affiliates from all fines, penalties and all associated expenses arising out of or resulting from its violation of any of its obligations in this Clause 25.

  - Each party may terminate the Agreement and each party to a Work order may terminate the Work Order(s) and to recover from the other party as a debt the amount of any loss or damage resulting from such a termination if any member of it or its Affiliates commits an act which it has undertaken not to commit as included in this Clause 25, whether or not such act was committed before, on or after the date of this Work Order/Agreement.

- The Contractor shall strictly comply with Contractor’s Safety Guidelines, Project HSE Specification and Consequence Management (electronic copy provided) and all other local regulations which may be in force from time to time.

- Confidentiality

The Contractor shall undertake to maintain strict confidentiality and refrain from disclosure thereof, of all Contract documents, Drawings and the Employer’s operations and affairs as private and confidential information & data shall not publish or disclose the same or any particulars thereof in any trade or technical paper or elsewhere without the consent in writing of the Employer to the third parties.

Contractor shall be responsible to ensure maintenance of such confidentiality in respect of their behalf and on behalf of their employees, representatives and associates involved in related activities. If any dispute arises as to the necessity of any publication or disclosure for the purpose of the Contract the same shall be referred to the decision of the Employer whose decision shall be final.

- Responsible Procurement

  - The Supplier shall comply with all applicable laws, rules, & regulations, Orders. conventions, or ordinances of the country(ies) where Services/Work is performed or where Goods are produced and/or relate to the provision, licensing, approval or certification of the Services/Goods, including, but not limited to, those relating to occupational health and safety, environmental matters, wages, working hours and conditions of employment, sub-contractor selection discrimination, data protection and privacy. Further the Supplier shall respect and commit to implementing APMM's Supplier Code of Conduct ("the Code") as amended from time to time and found at; http://www.maersk.com/sustainability/pages/thirdpartycodeofconduct.aspx or alternatively an internationally recognized standard within the areas of human rights, anticorruption, environment and labour, such as but not limited to United Nations Global Compact (UNGC) and Supplier agrees to accommodate any potential audit pursuant to verification of the same by APMM or Buyer. The Supplier shell require their own suppliers to implement similar rules and as appropriate pass on such requirements to their sub suppliers and so on. The original English version of the Code (as of August 2013) shall prevail in case of any disputes or discussions concerning the content and obligations of either Party. The Supplier warrants that it will register itself in APMM's CSR system (www.MaerskResponsibleProcurement.com) within 14 days after the date of the last signature on the Agreement and shall - if subsequently requested by APMM - provide documentation necessary for APMM to evaluate Supplier's ability to meet the requirements listed in the Code. Should the Supplier be unable to meet the listed requirements, the Supplier will agree to develop and execute an improvement plan.

  - Buyer shall at any time and without notice have the right to appoint at its own cost, charge and expense a well reputed third-party auditor (hereinafter referred to as "Buyer's Auditor") to audit and verify all matters in connection with Supplier's compliance with the previous Clause.

  - Supplier shall cooperate with the Buyer's Auditor and provide access to all relevant sites, people, and interviews with workers and documents. If the Buyer's Auditor uncover(s) any material concern, Supplier shall without any undue delay present Buyer with an improvement plan which shall ensure that all concerns are dealt with and remediated in a manner satisfactory to Buyer. Supplier's repeated violation of the Code/UNGC/International Bill of Human Rights and/or its failure to collaborate with Buyer's Auditor during an audit and/or its failure to· collaborate with Buyer in implementing or developing improvement plans shall be considered a material breach of this Agreement.

  - If Supplier commits any such breach of or fails to observe or perform any material obligation contained in the Code/UNGC/International Bill of Human Rights, and/or any agreed improvement plan, and such breach or failure has not been remedied to the satisfaction of Buyer within twenty-eight (28) days of receipt by the Supplier of a notice from Buyer requiring Supplier to remedy the same (or such longer period as may be specified in the said notice), Buyer shall be entitled to terminate the Contract in accordance with Clause of this agreement-work order.

- Compliance of Statutes, Laws, Rules, Regulations, etc.

The Contractor shall comply with all statutory requirements under the Labour laws, the Provision of Factory Act, Wages Act, Workers Compensation Act, Provident Fund and other applicable statutes, rules, regulations, laws, bye laws of the Government of Gujarat and Government of India. The Contractor shall indemnify and keep the employer indemnified against all consequences arising from breach of any of the said statutes, rules, regulations, laws, bye laws by the Contractor. The Contractor shall comply and submit all documents such as Labour License, Workman Compensation Insurance policy, Proof of Provident Fund of manpower, wages register etc before starting the work.

- Stamp Duty

The Stamp Duty for this Agreement shall be borne by the Contractor. If any dispute arises under this Agreement, the Contractor shall solely responsible to complete the compliances under stamp duty liability as per law.

- In consideration of the payments to be made by the Employer to the Agreement as hereinafter mentioned the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Agreement.

- The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price and such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

- Indemnity

Unless and otherwise any provision described in contrary to the provisions of this agreement, the provisions on indemnity events shall be in accordance with provisions of clause 30.2 of condition of contract.

- Force Majeure

Unless and otherwise any provision described in contrary to the provisions of this agreement, the provisions on indemnity events shall be in accordance with provisions of clause 47 of condition of contract.

- No Third-Party Rights

- This Agreement is not intended to nor shall it create any rights, claims or benefits enforceable by any person who is not a party to it. Accordingly, save to the extent expressly set out in this Agreement, no person shall derive any benefit or have any right or entitlement in relation to this Agreement.

- Assignment

- Neither Party may assign or transfer this Agreement or any part of its rights or obligations under this Agreement without the prior written consent of the other Party.

- Governing Law

- This Agreement shall be governed by and construed in accordance with the laws of India and subject to the provisions of Clause 30.4 relating to Arbitration, the courts at Ahmedabad only shall have exclusive jurisdiction to deal with all matters arising out of this Agreement.

- Termination

Unless and otherwise any provision described in contrary to the provisions of this agreement, either party may terminate this agreement in accordance with provision of Clause 46 of conditions of contract.

- Dispute Resolution

All dispute, differences, controversies and questions directly or indirectly arising at any time under, out of, in connection with or in relation to this Agreement including, without limitation, all disputes, differences, controversies and questions relating to the validity, interpretation, construction, performance and enforcement of any provision of this Agreement shall be finally, exclusively and conclusively settled by reference to arbitration under the  Arbitration & Conciliation Act, 1996.

The tribunal shall consist of a sole arbitrator appointed by the employer in mutual agreement with the contractor. The arbitration proceedings shall be conducted at Ahmedabad in the English language.

The court at Ahmedabad shall alone have exclusive jurisdiction in respect of the Arbitration.

- Notices

- If not provided for differently in this Agreement all notices, consents, demands or permissions permitted or required under this Agreement must be in writing and shall be considered given upon personal delivery of the written document or when received by the other party by registered mail or a reputable courier company and addressed to

The Employer				The Contractor

Gujarat Pipavav Port Limited		……………………

- Port Rampara-2				…………………………

- Via Rajula					………………………….

- District Amreli				………………………….

- Pipavav Port 365560			…………………………..

- Padminikant.mishra@apmterminals.com	…………………………..

- Padminikant Mishra				…………………………..

- Chief Operating Officer			…………………………..

- If either Party wishes to change its address for communication, it shall give to the other not less than five (5) days' notices in writing of such change.

- All notices and documents to be given or delivered pursuant to or otherwise in relation to this Agreement shall be in English language or be accompanied by a certified English translation.

- The employer shall in any event be discharged of all liability whatsoever and howsoever arising in respect of this agreement/contract unless legal proceedings are commenced and written notice thereof given to employer within twelve (12) months from the date of the loss, damage, delay or failure to adhere to any timeframe alleged to give rise to a claim.

IN WITHNESS whereof the parties hereto have caused this Agreement to be executed the day and year first before written in accordance with their respective laws.

SIGNED, SEALED AND DELIVERED

| By the said : The Employer (Gujarat Pipavav Port Limited) |  | By the said : The Contractor (…………………………………………………………) |
| --- | --- | --- |
| ________________________________ |  | ________________________________ |
| Name: Designation: |  | Name: Designation: |
| On behalf of the Employer in the presence of |  | On behalf of the Contractor in the presence of : |
| ________________________________ |  | ________________________________ |
| Name: Designation: |  | Name: Designation: |
| Gujarat Pipavav Port Limited, Post Rampara No. 2, Via Rajula, District Amreli, Pipavav Port, Gujarat - 365 560 |  | ……………………………………………………………………………………………………………………….……………………………………………………………… |

Date : …………………

Place : ……………….

##### GUJARAT PIPAVAV PORT LIMITED

DESIGN PROCURE AND CONSTRUCTION NEW CANTEEN FACILITY AT APM TERMINALS PIPAVAV

##### CONDITIONS OF CONTRACT

##### PART I – GENERAL CONDITIONS OF CONTRACT

The Conditions of Contract, Part I – General Conditions of Contract shall be those forming Part I of the “Conditions of Contract for Plant and Design Build” first edition 1999, with further amendments, prepared by the Fédération Internationale des Ingénieurs-Conseils (FIDIC). These Conditions are subject to the variations and additions set out in Part II hereof entitled “Particular Conditions of Contract.”

The FIDIC “Conditions of Contract for Plant and Design - Build”, mentioned above are not included with the present Bid Documents. Copies of the FIDIC “Conditions of Contract for Plant and Design - Build” can be obtained from the:

FIDIC Secretariat and Bookshop Geneva Airport

Box 311, 29 Route de Pré-Bois, Cointrin CH-1215 Geneva 15

Switzerland

Tel		: + 41 22 799 49 00	Fax	:+ 41 22 799 49 01

Website	:  www.fidic.org		E mail	: fidic.pub@fidic.org

##### PART II – PARTICULAR CONDITIONS OF CONTRACT

The Part II – Particular Conditions of Contract (PCC) constitute amendments and additions to the Part I – General Conditions of Contract (GCC). Clause numbers in this part correspond to those in the Part I – GCC, except for clauses with numbers higher than 20.8. Clauses, having numbers higher than 20.8, are to be construed as additional clauses to the Part I – GCC.

In the event of a conflict or inconsistency between the Part I (GCC) and the Part II (PCC), the provisions stipulated in the Part II (PCC) shall prevail over and supersede those of Part I (GCC).

| Clause – 1 : General Provisions |  |
| --- | --- |
| ##### Sub-Clause 1.1.3 Dates, Tests, Periods and Completion | Delete the Sub-Clause 1.1.3.7 and substitute: 1.1.3.7 "Defects Notification Period" means the period for notifying defects in the Works or a Section (as the case may be) under Sub-Clause 11.1 [Completion of Outstanding Work and Remedying Defects], as stated in the Appendix to Tender (with any extension under Sub-Clause 11.3 [Extension of Defects Notification Period]), calculated from the date on which the Works or Section is completed as certified under Sub-Clause 10.1 [Taking Over of the Works and Sections]. and which shall extend for a period of 24 months unless otherwise specified. |
| ##### Sub-Clause 1.1.6 Other Definitions | Delete the Sub-Clause 1.1.6.8 and substitute: 1.1.6.8 "Unforeseeable" means not reasonably foreseeable by the Date for the Return of Priced Tenders. Add the following after 1.1.6.9 in the Sub-Clause: 1.1.6.10 "Management Meeting" means a meeting called by either the Engineer or the Contractor's Representative in accordance with Sub-Clause 3.6. |
| ##### Sub-Clause 1.1.6.10 Third Party Code of Conduct | Add the following new Sub-Clause 1.1.6.10 after Sub-Clause 1.1.6.9 “Third Party Code of Conduct” means the APM Terminals Third Party Code of Conduct as included in Appendix A100_5. |
| ##### Sub-Clause 1.1.6.11 Employer’s Auditor | Add the following new Sub-Clause 1.1.6.11 after Sub-Clause 1.1.6.10 “Employer’s Auditor” means an internationally reputed third-party auditor, appointed by the Employer at his own cost, charge and expense. |
| ##### Sub-Clause 1.2 Interpretation | Add the following after (d) in the Sub-Clause: - The word "Tender" is synonymous with "Bid". Add the following at the end of the Sub-Clause: In these Conditions, provisions including the expression "Cost plus reasonable profit" require this profit to be (5%) of this Cost. |

| ##### Sub-Clause 1.8 ##### Care and Supply of Document | Delete the last paragraph of the Sub-Clause and substitute: If a Party becomes aware of an error or defect in a document which was prepared for use in executing the Works, the Party shall promptly give notice to the other Party of such error or defect. |
| --- | --- |
| ##### Sub-Clause 1.9 ##### Errors in the Employer Requirements | Add the following at the end of the Sub-Clause: I If the error occurred is due to design fault of the Contractor then Client shall not pay any amount on error construction & will be solely responsibility of the Contractor. |
| ##### Sub-Clause 1.12 ##### Confidential Details | Add the following new paragraph at the end of the Sub-Clause: The Contractor shall treat the details of the Contract and the Employer’s operations and affairs as private and confidential, save in so far as may be necessary for the purposes the Contract, and shall not publish or disclose the same or any particulars thereof in any trade or technical paper or elsewhere without the previous consent in writing of the Employer or the Engineer. If any dispute arises as to the necessity of any publication or disclosure for the purpose of the Contract the same shall be referred to the decision of the Employer whose award shall be final. The Confidentiality provision shall extend to the Contractor and Contractor’s Personnel. |
| ##### Sub-Clause 1.13 Compliance with Laws | In sub-paragraph (b) after “the Laws” INSERT “or Contract”. At the end of Sub-Clause 1.13 INSERT: (c) The business contact information regarding a Party’s personnel and/or third parties engaged by it may be shared for the purposes of maintaining the contractual business relationships between the Parties, e.g. contract management of the contract, payments and/or business development. The Parties shall handle such business contact information according to their privacy policies and practices. It is each Party’s responsibility to have a legal basis (i.e. privacy notice, consent, etc.) for sharing such business contact information with the other party. Maersk’s global privacy policy is available at www.maersk.com. The Parties may transfer such information to any country where their global organization operates and hereby authorizes such transfer per se and on behalf of such personnel and/or third parties. If required by applicable laws, the Parties agree to sign any additional document required to allow the transfer of such data outside its country of origin. In the event of any difference between the Contract and the any applicable law, the requirement for the stricter obligation or standard shall prevail. |
| Clause – 2 : The Employer |  |
| ##### Sub-Clause 2.1 ##### Right of Access to the Site | Delete the second paragraph of the Sub-Clause and substitute: If no such time is stated in the Appendix to Tender, the Employer shall give the Contractor right of access to, and possession of, the Site within such times as may be required to enable the Contractor to proceed without disruption in accordance with the programme submitted under Sub-Clause 8.3 (Programme). |
| ##### Sub-Clause 2.4 Employer’s Financial Arrangements | Delete the last sentence of the Sub-Clause and substitute: Before the Employer makes any material change to his financial arrangements, the Employer shall give notice to the Contractor with detailed particulars. |
| ##### Sub-Clause 2.5 Employer’s Claims | Delete the whole Sub-Clause and substitute: If the Employer considers himself to be entitled to any payment under any Clause of these Conditions or otherwise in connection with the Contract, and/or to any extension of the Defects Notification Period, the Employer or the Engineer shall give notice to the Contractor. However, notice is not required for payments due under Sub-Clause 4.19 [Employer's Equipment and Free-Issue Material], or for other services requested by the Contractor. The notice shall be given as soon as practicable after the Employer became aware of the event or circumstances giving rise to the claim. A notice relating to any extension of the Defects Notification Period shall be given before the expiry of such period. Within 42 days of the notice, the Employer shall provide particulars specifying the Clause or other basis of the claim and shall include substantiation of the amount and/or extension to which the Employer considers himself to be entitled in connection with the Contract. The Engineer shall then proceed in accordance with Sub-Clause 3.5 [Determinations] to agree or determine (i) the amount (if any) which the Employer is entitled to be paid by the Contractor, and/or (ii) the extension (if any) of the Defects Notification Period in accordance with Sub-Clause 11.3 [Extension of Defects Notification Period] included as a deduction in the Contract Price and Payment Certificates. The Employer shall only be entitled to set off against or make any deduction from an amount certified in a Payment Certificate, or to otherwise claim against the Contractor, in accordance with this Sub-Clause. |

| Clause – 3 : The Engineer |  |
| --- | --- |
| ##### Sub-Clause 3.1 Engineer's Duties and Authority | Delete the third paragraph of the Sub-Clause and substitute: The Engineer may exercise the authority attributable to the Engineer as specified in or necessarily to be implied from the Contract. If the Engineer is required to obtain the approval of the Employer before exercising a specified authority, the requirements shall be as stated in the Particular Conditions. The Employer shall promptly inform the Contractor of any change to the authority attributed to the Engineer. Add the following new paragraphs at the end of the Sub-Clause: The Engineer shall obtain the specific approval of the Employer before taking any of the following actions: - certifying additional cost determined under Clause 4.12; - issuing a variation under Clause 13, except: - in an emergency situation, as reasonably determined by the Engineer; or - as stipulated in the Appendix to Tender; - fixing rates or prices under Clause 12.3. Notwithstanding the obligation, as set out above, to obtain approval, if, in the opinion of the Engineer, an emergency occurs affecting the safety of life or of the Works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibilities under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Engineer, be necessary to abate or reduce the risk. The Contractor shall forthwith comply, despite the absence of approval of the Employer, with any such instruction of the Engineer. The Engineer shall determine an addition to the Contract Price, in respect of such instruction, in accordance with Clause 12.3 and shall notify the Contractor accordingly, with a copy to the Employer. |
| ##### Sub-Clause 3.4 Replacement of the Engineer | Delete the last sentence of the Sub-Clause and substitute: If the Contractor considers the intended replacement to be unsuitable, he has the right to raise reasonable objection against him by notice to the Employer, with supporting particulars, and the Employer shall give full and fair consideration. |

| ##### Sub-Clause 3.6 Management Meetings | Add the following new Sub-Clause after Sub-Clause 3.5: The Engineer may require the Contractor to attend a management meeting in order to review the arrangements for the Works. The Engineer shall record the minutes of meeting and circulate copies of the record to those attending the meeting and to the Employer. In the record, responsibilities for any actions to be taken shall be in accordance with the Contract. |
| --- | --- |
| Clause – 4 : The Contractor |  |
| ##### Sub-Clause 4.1 Contractor’s General Obligations | At the end of Sub-Clause 4.1 INSERT: Any documents other than Contractor’s Documents which are required to be submitted to the Engineer for approval under this Contract shall be submitted to the Engineer and the Engineer shall respond to the submittal within 14 days of receipt. If the document is returned to the Contractor marked as either “rejected” or “subject to comments”, then the Contractor shall resubmit the same to the Engineer within 7 days from receipt of the document, addressing the comments raised. The Engineer shall then respond within a further 7 days. For the avoidance of doubt, Contractor’s Documents shall be submitted for approval in accordance with Sub-Clause 5.2 [Contractor’s Documents]. |

| ##### Sub-Clause 4.2 Performance Security | Delete the second paragraph of the Sub-Clause and substitute: The Contractor shall deliver the Performance Security to the Employer within 14 days after receiving the Letter of Acceptance and shall send a copy to the Engineer. The Performance Security shall be issued by a well-known national/scheduled bank to be approved in advance in writing by the Employer and shall be in the form annexed as Section 5 or in another form approved by the Employer. Delete the fourth paragraph of the Sub-Clause and substitute: The Employer shall not make a claim under the Performance Security, except for amounts to which the Employer is entitled under the Contract. Add the following paragraph at the end of to this Sub-Clause: Without limitation to the provisions of the rest of this Sub-Clause, whenever the Engineer determines an addition or a reduction to the Contract Price as a result of a change in cost and/or legislation or as a result of a Variation amounting to more than 25 per cent of the portion of the Contract Price payable in a specific currency, the Contractor shall at the Engineer's request promptly increase, or decrease, as the case may be, the value of the Performance Security in that currency by an equal percentage. |
| --- | --- |
| ##### Sub-Clause 4.3 Contractor’s Representative | INSERT at the end of Sub-Clause 4.3: The Contractor's Representative and all these persons shall also be fluent in English. |
| ##### Sub-Clause 4.4 ##### Sub-Contractors | Add the following paragraphs at the end of this Sub-Clause: Prior consent shall not be required if the value of the subcontract is less than 0.01% of the Accepted Contract Amount. Where practicable, the Contractor shall give a fair and reasonable opportunity for contractors from India to be appointed as Subcontractors. |

| ##### Sub-Clause 4.7 Setting Out | Add the following paragraph at the end of the Sub-Clause: The Contractor shall give to the Engineer not less than 48 (Forty-Eight) hours’ notice of his intention to set out or give levels for any part of the Works so that timely arrangement may be made for checking or issuing instructions. He shall indicate therein by which date the information, if any is required by him. |
| --- | --- |
| ##### Sub-Clause 4.8 Safety Procedure | INSERT at the end of sub-paragraph (a) “and instructions from the Engineer” In sub-paragraph (c) after “obstruction” and before “so” INSERT “and keep Contractor’s Equipment in a state” Add the following paragraph at the end of the Sub-Clause: - ensure that all lights provided by the Contractor shall be screened so as not to interfere with any signal lights of the port or with any traffic or signal lights of any local or other authority; |
| ##### Sub-Clause 4.10 ##### Site Data | Add the following paragraph at the end of the Sub-Clause: Data made available by the Employer, in accordance with this Sub-Clause, shall be deemed to include data listed elsewhere in the Contract as open for inspection at the offices of: Gujarat Port Pipavav Limited Post Rampara-2, Via Rajula, District Amreli [Gujarat] Pipavav Port - 365 560 India |
| ##### Sub-Clause 4.12 Unforeseeable Physical Conditions | Delete the words “to the Engineer” in line 2 of the second paragraph and replace by “to the Employer and to the Engineer”. |
| ##### Sub-Clause 4.13 ##### Rights of Way and Facilities | Add the following paragraph at the end of the Sub-Clause: The Contractor shall apply to the Employer for the use of an area of land sufficient for the Contractor's work area, in close proximity to the Site. This work area shall be sufficient to accommodate the Contractor's site offices and all material storage, fabrication and testing facilities which the Contractor desires or which are required under the Contract. |
| ##### Sub-Clause 4.14 Avoidance of Interference | Add the following after the sub-clause (b): (c) the terminal operations of the Employer or of the other operators on the Site. |
| ##### Sub-Clause 4.15 Access Route | Add the following paragraph after the sub-clause (e): (f) The Contractor shall comply with all the access requirements of Site security / access / egress arrangements and in particular the requirements of the Employer. Add the following paragraphs at the end of the Sub-Clause: In case any operation connected with the traffic / access necessitates diversion, obstruction or closure of any road, railway or any other "right of way" the approval of the Engineer, the Employer and the respective competent authorities shall be obtained well in advance by the Contractor at their own costs. Access routes shall also include access by sea. The Contractor shall at all times observe and comply with all Laws, including regulations and orders relating to navigation and anchoring of floating plant to be used throughout the Works and any instruction that may be given by the Engineer. The Contractor shall carry out his work strictly in an approved manner and as agreed from time to time with the Employer and Engineer. |
| ##### Sub-Clause 4.18 Protection of the Environment | Delete the last paragraph and substitute: The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor's activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| ##### Sub-Clause 4.19 Electricity, Water and Gas | Delete the first paragraph and substitute: The Contractor shall, except as stated below, be responsible for the provision of all power, water and other services he may require for his construction activities and to the extent defined in the Specifications, for the tests. |
| ##### Sub-Clause 4.20 Employer’s Equipment and Free- Issue Material | Add the following paragraph at the end of the Sub-Clause: The Employer’s port operational equipment shall not be available to the Contractor unless authorization in writing is provided by the Employer and the Engineer. |
| ##### Sub-Clause 4.24 ##### Fossils | Delete the words “to the Engineer” in line 1 and 4 of the second paragraph and replace by “to the Employer and to the Engineer” |
| ##### Sub-Clause 4.25 Third Party Code of Conduct | Add the following new Sub-Clause 4.25 after Sub-Clause 4.24 The Contractor shall, in performing the Contract, adhere to the Third-Party Code of Conduct. In the event of any difference between the Contract and the Third-Party Code of Conduct, the document providing for the stricter obligation or standard shall prevail. |
| ##### Sub-Clause 4.26 Breach of Third-Party Code of Conduct | Add the following new Sub-Clause 4.26 after Sub-Clause 4.25 If the Contractor breaches the Third Party Code of Conduct or fails to collaborate with the Employer’s Auditor during an audit under Sub-Clause 4.28 [Compliance Auditing], and any such breach or failure has not been remedied to the satisfaction of the Employer within 28 days of receipt by the Contractor of a notice from the Employer requiring the Contractor to remedy the same (or such longer period as may be specified in the said notice), the Employer shall be entitled to terminate the Contract in accordance with Sub-Clause 15.2 [Termination by Employer]. |
| ##### Sub-Clause 4.27 Anti-Corruption and Export Control Compliance | Add the following new Sub-Clause 4.27 after Sub-Clause 4.26 The Contractor shall, in performing the Contract, undertake and represent that it and all of its affiliates, directors, officers or sub-contractors will comply in all material respects with all applicable laws, rules, regulations or similar instruments including relating to anti-corruption, competition law and foreign trade controls (export controls and sanctions laws of the UN, the EU and US or other relevant regulator) and shall promptly notify the Employer in case it becomes aware or receives notice of a (alleged) violation of any applicable law. For the purposes of clarity: - The Contractor will not give, promise or attempt to give or approve the giving of anything of value to any person, for illegal purposes or for improperly obtaining or retaining business. - The Contractor shall not deal, or cause the Employer to deal with, any person or entity in respect of transactions prohibited by foreign trade controls, except with Employer’s prior written consent; or which could damage the Employer’s commercial or other reputation interests, even if not in violation of any foreign trade controls. The Contractor has established processes, shall maintain policies and procedures to prevent violation of this Sub-Clause, and the Contractor shall maintain adequate records to verify and demonstrate its compliance with these provisions. The Contractor shall, upon written request from the Employer, confirm in writing its compliance with any of the provisions in this Sub-Clause 4.27 and provide any demonstration or proof of compliance as requested. If the Contractor breaches any of its obligations or representations in this clause, the Employer may terminate this Agreement with immediate effect without incurring any liability in accordance with Sub-Clause 15.2 (Termination by Employer) The Contractor shall indemnify, defend and hold harmless the Employer from all fines, penalties and all associated expenses arising out of or resulting from a violation of any of its obligations under this Sub-Clause 4.27. |
| ##### Sub-Clause 4.28 Compliance Auditing | Add the following new Sub-Clause 4.28 after Sub-Clause 4.27 The Employer shall have the right to appoint an Employer’s Auditor to audit and verify all matters in connection with the Contractor’s compliance with the Contract. The Contractor shall cooperate with the Employer’s Auditor, provide access to all relevant sites and arrange interviews with all relevant personnel of the Contractor or any Subcontractor. If the Employer’s Auditor determines any concerns, the Contractor shall without any undue delay present the Employer with an improvement plan, which shall ensure that all such concerns are dealt with and remediated in a manner satisfactory to the Employer. |
| Clause – 5 : Design |  |
| ##### Sub-Clause 5.4 Technical Standard & Regulations | INSERT between the first and second paragraph: The Contractor shall pass to the Engineer and Employer approvals received by the Contractor in connection with the Country's technical standards or Laws applicable to the Works. When requested to do so by the Engineer, the Contractor shall provide evidence that he has complied with all such technical standards and Laws. |
| Clause – 6 : Staff and Labour |  |
| ##### Sub-Clause 6.5 Working Hours | Delete the whole Sub-Clause and substitute: Working hours are unrestricted and assumed to be 24 hours per day 7 days per week unless otherwise governed by Laws and Regulations in India. |
| ##### Sub-Clause 6.7 ##### Health and Safety | Add the following sentence at the end of the second paragraph: The Contractor shall comply with all statutory requirements, the Employer’s safety policy and any reasonable direction issued by the Employer’s safety department or authorised personnel of the Employer as may be issued from time to time. The cost of the provision of all safety precautions, equipment and clothing shall be borne by the Contractor. All works shall be carried out in a safe manner and free from any danger and shall comply with the relevant Laws regarding safety of the Works. |

|  | All personnel who are in the work area and / or within the operations area of the Employer shall continually wear protection helmets and appropriate boots, and safety vests and belts when they are required by the Laws. Workers shall either wear high visibility vests or jackets or shall have appropriate high visibility adhesive stripes attached to their clothing. Life Jackets shall be worn by all staff working near and over water. The Contractor shall take all precautions necessary to protect the health and safety of persons where works may expose workmen and other persons on, or within the vicinity of the site, to conditions which are dangerous or potentially dangerous to health, including the noxious effects of dust, fumes, liquids, infection, fire, explosion, radiation, or other hazards. |
| --- | --- |
| ##### Sub-Clause 6.8 Contractors Superintendence | At the end of Sub-Clause 6.8 INSERT: A reasonable proportion of the Contractor's superintending staff shall be able to understand and communicate in English, Hindi or Gujarati. |
| ##### Sub-Clause 6.12 Employment of Local Personnel | Add the following new Sub-Clause 6.12 after Sub-Clause 6.11: The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour from sources within India. |
| ##### Sub-Clause 6.13 Foreign Staff and Labour | Add the following new Sub-Clause 6.13 after new Sub-Clause 6.12: The Contractor may import any personnel who are necessary for the execution of the Works. The Contractor must ensure that these personnel are provided with the required residence visas and work permits. The Contractor shall be responsible for the repatriation Contractor's non- local Personnel. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial. |
| ##### Sub-Clause 6.14 Measures against Insect and Pest Nuisance | Add the following new Sub-Clause 6.14 after new Sub-Clause 6.13: The Contractor shall at all times take the necessary precautions to protect all staff and labour employed on the Site from insect and pest nuisance, and to reduce their danger to health. The Contractor shall provide suitable prophylactics for the Contractor's Personnel and shall comply with all the regulations of the local health authorities, including use of appropriate insecticide. |
| ##### Sub-Clause 6.15 Alcoholic Liquor and Drugs | Add the following new Sub-Clause 6.15 after new Sub-Clause 6.14: The Contractor shall not, in accordance with the Laws of the Country, import, sell, give, barter or otherwise dispose of any alcoholic liquor or drugs, or permit or allow importation, sale, gift, barter or disposal by Contractor's Personnel. |
| ##### Sub-Clause 6.16 ##### Arms and Ammunition | Add the following new Sub-Clause 6.16 after new Sub-Clause 6.15: The Contractor shall not give, barter or otherwise dispose of to any person, any arms or ammunition of any kind, or allow Contractor's Personnel to do so. |
| ##### Sub-Clause 6.17 Festivals and Religious Customs | Add the following new Sub-Clause 6.17 after new Sub-Clause 6.16: The Contractor shall respect the Country's recognised festivals, days of rest and religious or other customs. |
| ##### Sub-Clause 6.18 Supply of Food stuffs | Add the following new Sub-Clause 6.18 after new Sub-Clause 6.17: The Contractor shall arrange for the provision of a sufficient supply of suitable food as may be stated in the Specification at reasonable prices for the Contractor's Personnel for the purposes of or in connection with the Contract. |
| ##### Sub-Clause 6.19 ##### Supply of Water | Add the following new Sub-Clause 6.19 after new Sub-Clause 6.18: The Contractor shall, having regard to local conditions, provide on Site an adequate supply of drinking and other water for the use of the Contractor's Personnel. |
| ##### Sub-Clause 6.20 ##### Funeral Arrangements | Add the following new Sub-Clause 6.20 after new Sub-Clause 6.19: The Contractor shall be responsible, to the extent required by local regulations, for making any funeral arrangements for any of his local employees who may die while engaged under the Works. |
| ##### Sub-Clause 6.21 Forced or Compulsory Labour | Add the following new Sub-Clause 6.21 after new Sub-Clause 6.20: The Contractor shall not employ "forced or compulsory labour" in any form. "Forced or compulsory labour" consists of all work or service, not voluntarily performed, that is extracted from an individual under threat of force or penalty. |
| ##### Sub-Clause 6.22 Prohibition of Harmful Child Labour | Add the following new Sub-Clause 6.22 after new Sub-Clause 6.21: The Contractor shall not employ any child to perform any work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. |
| ##### Sub-Clause 6.23 Employment Records of Workers | Add the following new Sub-Clause 6.23 after new Sub-Clause 6.13: The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked, and wages paid to all workers. These records shall be summarised on a monthly basis and shall be available for inspection by the Engineer, during normal working hours. These records shall be included in the details to be submitted by the Contractor under Sub-Clause 6.10 Records of Contractor's Personnel and Equipment. The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour with appropriate qualifications and expertise from sources within the Country. |
| Clause – 7 : Plant, Material and Workmanship |  |
| ##### Sub-Clause 7.6 Remedial Work | Add the following paragraph at the end of the Sub-Clause: In addition to the costs for the removal of improper work, materials or plant, the Contractor shall be liable for the additional costs of the Engineer's services in supervising and administering these works. These costs shall be determined as the additional amount charged by the Engineer to the Employer for the provision of engineering services related to this item. |
| Clause – 8 : Commencement, Delays and Suspension |  |
| ##### Sub-Clause 8.1 Commencement of Work | In the second sentence delete “42 days” and insert “14 days”. |

| ##### Sub-Clause 8.3 Programme | Delete the first paragraph and substitute: The Contractor shall submit a detailed time programme to the Engineer within 7 days after receiving the notice under Sub-Clause 8.1 (Commencement of Works). The Contractor shall also submit a revised programme whenever the previous programme is inconsistent with actual progress or with the Contractor's obligations including whenever the Engineer has granted an extension of time to complete the Works under Sub-Clause 3.5 and 20.1. Add the following paragraphs at the end of the Sub-Clause: For the avoidance of doubt, the Contractor will only be entitled to an extension of Time for Completion provided it has made all reasonable proper efforts to mitigate any delay. Any failure by the Employer to rely upon any antecedent breach of a condition precedent will not amount to a waiver by the Employer of its rights in this respect. Further, where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is a cause of delay which would not entitle the Contractor to an extension of time then to the extent that the delays are concurrent, the Contractor will not be entitled to an extension of time. |
| --- | --- |
| ##### Sub-Clause 8.4 Extension of Time for Completion | At the end of Sub-Clause 8.4 INSERT: For the avoidance of doubt, the Contractor will only be entitled to an extension of Time for Completion provided it has made all reasonable efforts to mitigate any delay. |
| ##### Sub-Clause 8.5 Delay Caused by Authority | At the end of Sub-Clause 8.5 INSERT: Further, where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is a cause of delay which would not entitle the Contractor to an extension of time then to the extent that the delays are concurrent, the Contractor will not be entitled to an extension of time. |
| ##### Sub-Clause 8.7 ##### Delay Damages | Add the following paragraphs at the end of the Sub-Clause: If the Engineer extends the Time for Completion under Sub-Clause 8.4 after delay damages have been paid or otherwise accounted for under this Sub- Clause, the extension of the Time for Completion shall not invalidate the Employer's claim for delay damages. In such circumstances the Contractor's liability to pay delay damages shall be limited to the sum due on the basis of the new Time for Completion, and the Employer shall repay or otherwise account for the difference between that sum and the sum which has been paid or otherwise accounted for on the basis of the Employer's claim before the extension of the Time for Completion. Interest shall not be payable by the Employer on any amounts payable or repayable under this Sub-Clause. Once the applicable limit of delay damages is reached, the Employer will be able to suspend this contract and hire third parties to complete the Works. Any cost associated with the hiring of third parties to complete the Works shall be recovered from the Contractor. |
| ##### Sub-Clause 8.8 Suspension of Work | At the end of Sub-Clause 8.8 INSERT: Without prior written approval from Engineer to do otherwise, throughout any suspension, the Contractor will maintain its staff and labour resources ready to recommence work, unless agreed otherwise with the Engineer. The Contractor will notify the Engineer of details of any of its staff and labour that it proposes to redeploy to other projects and the Engineer may instruct the Contractor not to so redeploy any staff or labour it considers to be key to the project. |
| ##### Sub-Clause 8.9 Consequences of Suspension | At the end of Sub-Clause 8.9. INSERT: If the Engineer suspends progress of part or all of the Works in order to mitigate or prevent a risk to the environment or to the health or safety of Contractor’s Personnel, visitors, and adjacent communities to the Site, the Contractor shall not be entitled either to an extension of time for, or to payment of the Cost incurred in relation to that. |
| ##### Sub-Clause 8.11 Prolonged Suspension | Substitute the wording of the last sentence with: “If the suspension affects the whole of the Works and the suspension has continued for an uninterrupted period of 90 days the Contractor may give notice of termination under Sub-Clause 16.2 [Termination by Contractor]”. |
| Clause – 9 : Tests on Completion |  |
| ##### Sub-Clause 9.1 Contractor’s Obligations | Delete the first paragraph and substitute: The Contractor shall carry out the Tests on Completion required by the Specification in accordance with this Clause and Sub-Clause 7.4 [Testing], after providing the documents in accordance with Sub-paragraph (d) of Sub- Clause 4.1 [Contractor's General Obligations]. |
| Clause – 12 : Tests after Completion |  |
| ##### Sub-Clause 12.4 Failure to pass tests after completion | DELETE the first paragraph. This Sub-Clause shall now commence “If the Works, or a Section……” |
| Clause – 13 : Variation & Adjustment |  |
| ##### Sub-Clause 13.1 ##### Right to Vary | Add the following paragraph at the end of the Sub-Clause. The alteration, additions and improvements under this Sub-Clause shall be made only insofar as they can be executed by means of the Contractor's Equipment used or intended to be used in the execution of the Works as originally specified by the Contractor in his bid document. The Employer reserves the right to reduce or delete certain aspects of the Works including items of the Works specified as “Optional” during the construction period by informing the Engineer and Contractor in writing of proposed changes. Calculation of the amended value of work reduced or deleted shall be based on measured work at the rate defined in the Schedules. |
| Clause – 14 : Contract Price and Payment |  |
| ##### Sub-Clause 14.2 Advance Payment | Delete the last sentence of the third paragraph and substitute: This guarantee shall be in the form annexed as Annex III issued by a reputable national/schedule bank to be approved in advance in writing by the Employer. |

| ##### Sub-Clause 14.16 Dues and Duties | Add the following new Sub-Clause 14.16 after new Sub-Clause 14.15: The Contractor shall pay, such rates and prices defined by him in the Contract Price which shall include but not limited, all freight and insurance charges, harbour dues, pilotage, wharfage, port rates, tolls landing charges, octroi and all other dues in respect of plant and equipment, ancillaries, spares, lubricants, etc imported into India and brought into Gujarat in connection with the Works. This is excluding any port charges which will otherwise be levied by the Gujarat Pipavav Port Limited. |
| --- | --- |
| ##### Sub-Clause 14.17 Local Taxation | Add the new Sub-Clause 14.17 after Sub-Clause 14.16: The Contract Price shall be exclusive of Gujarat/Central Goods Service Tax, but include all customs duties, import duties, business taxes, and income and other taxes duties, cess, Labour cess, levies, royalties, etc. that may be levied in accordance with the laws and regulations in being on the date 28 days prior to the latest date for submission of bids in the Employer's country on the Contractor's Equipment, and supplies (temporary and consumable) acquired for the purpose of the Contract and on the services performed under the Contract. Nothing in the Contract shall relieve the Contractor from his responsibility to pay any tax that may be levied in the Employer's country on profits made by him in respect of the Contract. |
| ##### Sub-Clause 14.18 Personal Income Taxes | Add the new Sub-Clause 14.18 after Sub-Clause 14.17: The Contractor's Personnel will be liable to pay personal income taxes in the Employer's country in respect of such of their salaries and wages as are chargeable under the laws and regulations for the time being in force, and the Contractor shall perform such duties in regard to such deductions thereof as may be imposed on him by such Laws and regulations. |
| Clause – 15 : Termination by Employer |  |
| ##### Sub-Clause 15.2 Termination by Employer | At the end of Paragraph 5, add the words “The Contractor shall promptly remove all of the Contractor’s Equipment from the Site.” |

| ##### Sub-Clause 15.5 Employer’s Entitlement to Termination | Add the following paragraphs at the end of the Sub-Clause: If the Employer determines that the Contractor has engaged in corrupt, fraudulent, collusive or coercive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days' notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of Clause 15 shall apply as if such expulsion had been made under Sub-Clause 15.2 (Termination by Employer). Should any employee of the Contractor be determined to have engaged in corrupt, fraudulent or coercive practice during the execution of the Works then that employee should be removed in accordance with Sub-Clause 6.9 [Contractor's Personnel]. |
| --- | --- |
| Clause – 16 : Suspension and Termination by Contractor |  |
| ##### Sub-Clause 16.1 Contractors Entitlement to Suspend Work | DELETE in the first paragraph “or the Employer fails to comply with Sub-Clause 2.4 [Employer's Financial Arrangements]” Delete the words “to the Engineer” in line 3 of the fourth paragraph and replace by “to the Employer and to the Engineer”. |
| ##### Sub-Clause 16.2 Termination by Contractor | DELETE sub-paragraph (a). |
| ##### Sub-Clause 16.4 Payment on Termination | In sub-paragraph (c) DELETE “loss of profit or other loss or”. |
| Clause – 17 : Risk & Responsibility |  |
| ##### Sub-Clause 17.1 Indemnities | INSERT sub-paragraph (c) as follows: - and, any breach by the Contractor of its obligations under Sub-Clauses 4.25 [Third Party Code of Conduct], 4.26 [Breach of Third-Party Code of Conduct] or 4.27 [Export Control]. |
| ##### Sub-Clause 17.3 Employers Risks | At the end of the first sentence INSERT “insofar as they directly affect the execution of the Works in the Country”. |
| ##### Sub-Clause 17.4 Consequences of Employer’s Risks | Delete the words “to the Engineer” in line 3 of the first paragraph and line 2 of the second paragraph and replace by “to the Employer and to the Engineer”. |

| ##### Sub-Clause 17.6 Limitation of Liability | In the first line of the second paragraph, insert “cumulative” after the word “total”. At the end of the second paragraph, replace the words “the sum stated in the Particular Conditions or (if a sum is not so stated) the Accepted Contract Amount” with the words “ten percent (10%) of the Contract Price, including without limitation Delay Damages. The foregoing is without prejudice to the right of Contractor to avail itself of the benefits of the Convention on Limitation of Liability for Maritime Claims”. At the end of Sub-Clause 17.6 INSERT: This Sub-Clause shall not apply to a breach by the Contractor of any of Sub-Clauses 1.13 [Compliance with Laws], 4.25 [Third Party Code of Conduct], 4.26 [Breach of Third-Party Code of Conduct] or 4.27 [Export Control]. |
| --- | --- |

| Clause – 18 : Insurance |  |
| --- | --- |
| ##### Sub-Clause 18.2 Insurance for Works and Contractors Equipments | DELETE the entire Sub-Clause and SUBSTITUTE: The insuring Party shall insure the Works, Plant, Materials and Contractor’s Documents for not less than the full Accepted Contract Amount and including a provision for the costs of demolition, removal of debris, professional fees and profit. This insurance shall be effective from the Commencement Date until the date of issue of the Taking-Over Certificate for the Works. The insuring Party shall maintain this insurance to provide cover until the date of issue of the Performance Certificate, for loss or damage for which the Contractor is liable arising from a cause occurring on the Site, including storage, disposal, borrow pit and any other working areas, after the Commencement Date and prior to the issue of the Taking-Over Certificate, and for loss or damage caused by the Contractor on the Site, including storage, disposal, borrow pit and any other working areas, in the course of any other operations (including those under Clause 11 [Defects Liability] and Clause 12 [Tests after Completion]). The insuring Party shall insure the Contractor's Equipment for not less than the full replacement value, including delivery to Site. For each item of Contractor's Equipment, the insurance shall be effective while it is being transported to the Site and until it is no longer required as Contractor's Equipment. If the Contractor’s Equipment includes vessels, items of floating equipment or watercraft, the insuring Party shall effect, or require that the owners effect, and maintain charterer’s liability insurance, customary material damage, hull and machinery insurance with limits of liability of the full replacement cost of the vessel, items of floating equipment or watercraft, and protection and indemnity insurance for a limit of not less than USD 5,000,000 for any one occurrence or series of occurrences arising out of one event. Unless otherwise stated in the Particular Conditions, insurances under this Sub-Clause: - in relation to the Works, Plant, Materials and Contractor’s Documents located on the Site, including storage, disposal, borrow pit and any other working areas, shall be effected and maintained by the Employer as insuring Party; |

|  | - in relation to the Plant, Materials and Contractor’s Documents located off the Site, including in the course of transit to and from the Site within the Country, shall be effected and maintained by the Employer as insuring Party. For transit to and from locations outside the Country, the Contractor shall be the insuring Party, naming the Employer and Lenders as co-insured. In the event of transits of any Plants and Materials critical to the timely completion of the Project, the Employer reserves the right to be the insuring Party; - in relation to the Contractor's Equipment, shall be effected and maintained by the Contractor as insuring Party; and - coverage for the Works, Plant, Materials and Contractor’s Documents shall be in the joint names of the Parties, who shall be jointly entitled to receive payments from the insurers, payments being held or allocated between the Parties for the sole purpose of rectifying the loss or damage. The Contractor shall bear the cost of any deductibles applying to any insurance claims made on the Employer’s insurance policies which arise from occurrences or events for which the Contractor is responsible under the contract or otherwise and shall, in making any claim, comply with the Employer’s insurance claims procedure. The Contractor shall make all of his Subcontractors and suppliers aware of this obligation. All insurances to be effected by the Employer under this contract shall be with insurers and on terms to be approved solely by the Employer. The Contractor shall be deemed to have satisfied himself and shall cause all of his Subcontractors and suppliers to satisfy themselves with regard to the extent of cover provided under the policies of insurance effected by the Employer. The Contractor is deemed to have read and understood all the terms of the insurance provided by the Employer. If, in the Contractor’s opinion, the amounts and/or risks insured are insufficient to cover the Contractor’s duties, obligations and liabilities under this contract or otherwise, the Contractor may effect such further insurance at Contractor’s own cost. The Contractor shall for himself and on behalf of all his Subcontractors and suppliers accept the insurance policies effected by the Employer as if they had been arranged by him directly and shall with all due diligence observe and fulfil and procure that his Subcontractors and suppliers observe and fulfil the terms contained in the said policies. Parties hereby agree that in any type of insurance as herein provided, the insurance institution shall waive its right to subrogate against the Employer in connection with the insurance. |
| --- | --- |
| ##### Sub-Clause 18.3 Insurance against Injury to Persons and Damage to Property | DELETE the entire sub-paragraphs (c) and (d) up to the end of the Sub-Clause. |

| ##### Sub-Clause 18.4 Insurance for Contractors Personnel | Delete the words “The Contractor” in line 1 of the first paragraph and replace by “Pursuant to Workers Compensation legislation or any other law amending or replacing such legislation, the Contractor”. Delete the second paragraph and substitute: The insurance shall cover the Employer and the Engineer against liability for claims, damages, losses and expenses (including legal fees and expenses) arising from injury, sickness, disease or death of any person employed by the Contractor or any other of the Contractor's Personnel, except this insurance may exclude losses and claims to the extent that they arise from any act or neglect of the Employer or the Employer's Personnel. Add the following paragraph at the end of the Sub-Clause: Provided the Contractor will not be required to take out any Workmen's Compensation Insurance Policy if the workers employed in the Works are eligible for coverage under any employee’s social security laws and regulations that may be in place and are so covered. The Contractor shall register his employees and contribute under the relevant social security scheme in the places where the scheme is implemented and comply with the provisions of the relevant laws and regulations. He shall submit the code Number and Insurance Numbers of all the workers on site to the Engineer for checking. |
| --- | --- |
| ##### Sub-Clause 18.5 Insurance for Design | Add the new Sub-Clause 18.5 after Sub-Clause 18.4: The Contractor shall effect professional indemnity insurance, which shall cover the risk of the Contractor being in breach of its design obligations in respect of the Works. This Insurance shall be for a limit of not less than USD 1,000,000 per occurrence. The Contractor shall maintain the professional indemnity insurance in full force and effect until five years after issue of the Taking-Over Certificate. The Contractor shall notify the Employer promptly of changes to this insurance. |
| ##### Sub-Clause 18.6 Additional Insurances | Add the new Sub-Clause 18.6 after new Sub-Clause 18.5: The Contractor shall effect and maintain, in full force until the works are delivered to Employer, subject to the terms set forth herein, the following insurances with a triple “A” insurance company, incorporated in the Country, satisfactory to Employer, duly authorized to do business in the Country: - Automobile liability Insurance against claims by third parties in respect of bodily injury (including death) and property damage arising out of and in connection with the use of all owned, leased, non-owned and hired vehicles used in connection with the performance of the Works in accordance with statutory obligations and for the following minimum limits: |

|  | - in respect of bodily injury (including death), on an unlimited basis; and - in respect of property damage, on a USD 1,000,000 any one occurrence unlimited as to the number of claims basis. - Civil liability caused by cargo in transit including hazardous cargo As regards to cargo vehicles that transport raw materials, equipment and/or materials used in the construction of the Works, same shall have the coverage of civil liability for damages related to the cargo, and if required by the scope of the construction works as provided in these Conditions, it shall have coverage of civil liability for any for hazardous cargo. This insurance shall be in an amount not less than the responsibility limits of USD 1,000,000 per occurrence or arising from same event and shall include a contractual liability insurance applicable to Contractor’s obligations. |
| --- | --- |
| ##### Sub-Clause 18.7 Professional Indemnity Insurance | Add the following new Sub-Clause 18.7 after new Sub-Close 18.6: The Contractor shall provide Professional Indemnity Insurance in accordance with the following requirements: - Cover: Professional Indemnity Insurance to be maintained on an annually renewable basis in respect of or in connection with the performance of the Contractor’s design obligations under the Contract or at Law with a limit of indemnity of not less than as stated in Appendix of Tender for any one occurrence or a series of occurrences out of any one event in respect of any negligence (which for the avoidance of doubt shall include any negligence act error omission or default) on the part of the Contractor. Such insurance shall not exclude pollution or contamination. The Contractor shall immediately inform the Employer if such insurance ceases to be available or is otherwise not maintained in accordance with this clause or for any reason becomes void or unenforceable. In the event that such insurance cover ceases to be available or becomes void or unenforceable the Contractor shall, subject to obtaining the prior agreement in writing of the Employer to such reduced level of insurance cover, maintain professional indemnity insurance at the maximum level of cover which is available. - Period of Insurance: During the Contract Period and thereafter for a period of two years after issue of the performance Certificate for the Works |

| ##### Sub-Clause 18.8 ##### War Risk Insurance | Add the following new Sub-Clause 18.8 after new Sub-Close 18.7: If the Contractor receives instructions from the Employer to insure against War Risk, such insurance if available shall be effected, at the cost of the Employer, with an Insurance Company acceptable to the Employer and shall be in the joint names of the Contractor and the Employer. |
| --- | --- |
| Clause – 20 : Claims, Disputes and Arbitration |  |
| ##### Sub-Clause 20.1 Contractors Claims | After sub-paragraph (c) INSERT: If the Contractor fails to submit claim within the 42 day period described above, a detailed claim including supporting particulars of the basis of the claim and of the extension of time and/or additional payment claimed, then the Time for Completion shall not be extended, the Contractor shall not be entitled to additional payment and the Employer shall be discharged from all liability in connection with the claim. Before the final paragraph INSERT: If the Engineer does not respond within such period, the Employer shall instruct the Engineer to do so, upon failure of which within the timeframe set by the Employer after consultation with the Contractor, the claim shall be deemed rejected by the Engineer and either Party may refer to the Dispute Adjudication Board in accordance with Sub-Clause 20.4 [Obtaining Dispute Adjudication Board's Decision]. |
| ##### Sub-Clause 20.2 Appointment of the Dispute Adjudication Board | In the first paragraph, DELETE the last sentence and SUBSTITUTE: “The Parties shall jointly appoint a DAB by the date stated in the Appendix to Tender.” In the sixth paragraph, after “the three members” and “shall be” INSERT: “, including remuneration of any expert whom the DAB consults,” After the sixth paragraph INSERT: If at any time the Parties so agree, they may jointly refer a matter to the DAB for it to give its opinion. Neither Party shall consult the DAB on any matter without the agreement of the other Party. DELETE the last paragraph and SUBSTITUTE: Unless otherwise agreed by both Parties, the appointment of the DAB (including each member) shall expire when the discharge referred to in Sub-Clause 14.12 [Discharge] shall have become effective. |

| ##### Sub-Clause 20.6 Arbitration | Add the following paragraph at the end of the Sub-Clause: The law governing this Clause 20 will be the governing law of the contract as stated in the Appendix to Tender. |
| --- | --- |
| ##### Sub-Clause 20.7 Failure to Comply with Dispute Adjudication Board’s Decision | Add the following paragraph at the end of the Sub-Clause: In the event that a Party fails to comply with a decision of the DAB, then the other Party may, without prejudice to any other rights it may have, refer the failure itself to arbitration under Sub-Clause 20.4 [Obtaining Dispute Adjudication Board's Decision] and Sub-Clause 20.5 [Amicable Settlement] shall not apply to this reference. |

Appendix to Tender

DESIGN, PROCURE AND CONSTRUCTION OF NEW CANTEEN FACILITY AT APM TERMINALS PIPAVAV

NOTE	with the exception of the items for which the Employer’s requirements have been inserted, the following information must be completed before the Tender is submitted)

| Item | Sub-Clause | Data |
| --- | --- | --- |
| Employer's name and address | 1.1.2.2 & 1.3 | Gujarat Pipavav Port Ltd Post Rampara-2 Via Rajula, Distt Amreli Pipavav Port – 365 560 Gujarat (India) T: +91 (0)2794-286001 F: +91 (0)2794-286312 |
| Contractor's name and address | 1.1.2.3 & 1.3 | […………………………………………………………………] |
| Engineer's name and address | 1.1.2.4 & 1.3 | Gujarat Pipavav Port Ltd Post Rampara-2 Via Rajula, Distt Amreli Pipavav Port – 365 560 Gujarat (India) T: +91 (0)2794-286001 F: +91 (0)2794-286312 |
| Time for Completion of the Works | 1.1.3.3 | 180 (One Hundred Eighty) Days from Handing of the Work Site |
| Defects Notification Period | 1.1.3.7 | 730 days from the date of Taking Over Certificate issued by the Employer |
| Electronic transmission systems | 1.3 | Email |
| Governing Law | 1.4 | Laws of India |
| Ruling language | 1.4 | English |
| Language for communications | 1.4 | English |
| Time for access to the Site | 2.1 | [………] days after Commencement Date |
| Amount of Performance Security | 4.2 | 10% of the Accepted Contract Amount, in the currencies and proportions in which the Contract Price is payable |
| Period for notifying unforeseeable errors, faults and defects in the Employer’s Requirements | 5.1 | 120 days |
| Normal working hours | 6.5 | Unrestricted, 24 hours a day, 7 days a week, subject to adherence and compliance of applicable Laws by the contractor |
| Commencement of Works | 8.1 | To be finalized. |
| Delay damages for the Works | 8.7 & 14.15(b) | 0.25% of the final Contract Price per day, |
| Maximum amount of delay damages | 8.7 | 10% of the final Contract Price |
| If there are Provisional Sums: Percentage for adjustment of Provisional Sums | 13.5(b) | 0 % |
| Adjustments for Changes in Cost | 13.8 | Not applicable |
| Total advance payment | 14.2 | 20% of the Accepted Contract Amount only against bank guarantee |
| Number and timing of instalments | 14.2 | 2 instalments: - 10% of Accepted Contract Amount as first advance payment - 10% after completion and erection of all site facilities for the Engineer and Employer (i.e. ready to occupy) |
| Currencies and proportions | 14.2 | 100% in Indian Rupees |
| Start repayment of advance payment | 14.2(a) | First Payment Certificate |
| Repayment amortisation of advance payment | 14.2(b) | 10% |
| Percentage of retention | 14.3 | 10% of each payment |
| Limit of Retention Money | 14.3 | 10% of the final Contract Price |
| If Sub-Clause 14.5 applies: |  |  |
| Plant and Materials for payment when shipped en route to the Site | 14.5(b) | ………………[list] ………………[list] |
| Plant and Materials for payment when delivered to the Site | 14.5(c) | ………………[list] ………………[list] |
| Minimum amount of Interim Payment Certificates | 14.6 | 5% of the Accepted Contract Amount |
| Currency of payment | 14.15 | Indian Rupees |
| Periods for submission of insurance: - evidence of insurance - relevant policies | 18.1 18.1 | Prior to mobilization Prior to mobilization |
| Maximum amount of deductibles for insurance of the Contractor’s 's risks | 18.2(d) | Nil |
| Minimum amount of third party insurance | 18.3 | 50 million Indian Rupees |
| Professional Indemnity Insurance | 18.6 | 50 million Indian Rupees |
| Date by which the DAB shall be appointed | 20.2 | within 28 days of request by either party |
| The DAB shall be | 20.2 | A DAB of three Members |
| Appointment (if not agreed) to be made by | 20.3 | The President of FIDIC or a person appointed by the President |

Annex A: Form of Parent Company Guarantee

This guarantee shall be printed on parent company letterhead.

Brief description of Contract		______________________________________________

Name and address of Employer	______________________________________________

___________________________________________ (together with successors and assigns).

We have been informed that _______________ (hereinafter called the ‘Contractor’) is submitting an offer for such Contract in response to your invitation, and that the conditions of your invitation require his offer to be supported by a parent company guarantee.

In consideration of you, the Employer, awarding the Contract to the Contractor, we (name of parent company) irrevocably and unconditionally guarantee to you, as a primary obligation, the due performance of all the Contractor's obligations and liabilities under the Contract, including the Contractor's compliance with all its terms and conditions according to their true intent and meaning.

If the Contractor fails to so perform his obligations and liabilities and comply with the Contract, we will indemnify the Employer against and from all damages, losses and expenses (including legal fees and expenses) which arise from any such failure for which the Contractor is liable to the Employer under the Contract.

This guarantee shall come into full force and effect when the Contract comes into full force and effect. If the Contract does not come into full force and effect within a year of the date of this guarantee, or if you demonstrate that you do not intend to enter into the Contract with the Contractor, this guarantee shall be void and ineffective. This guarantee shall continue in full force and effect until all the Contractor's obligations and liabilities under the Contract have been discharged, when this guarantee shall expire and shall be returned to us, and our liability hereunder shall be discharged absolutely.

This guarantee shall apply and be supplemental to the Contract as amended or varied by the Employer and the Contractor from time to time. We hereby authorise them to agree any such amendment or variation, the due performance of which and compliance with which by the Contractor are likewise guaranteed hereunder. Our obligations and liabilities under this guarantee shall not be discharged by any allowance of time or other indulgence whatsoever by the Employer to the Contractor, or by any variation or suspension of the works to be executed under the Contract, or by any amendments to the Contract or to the constitution of the Contractor or the Employer, or by any other matters, whether with or without our knowledge or consent.

This guarantee shall be governed by the law of the same country (or other jurisdiction) as that which governs the Contract and any dispute under this guarantee shall be finally settled under the Rules of Arbitration of the International Chamber of Commerce by one or more arbitrators appointed in accordance with such Rules. We confirm that the benefit of this guarantee may be assigned subject only to the provisions for assignment of the Contract.

Date _____________	Signature(s) ___________________________

Annex B: Form of Tender Security

This security shall be provided by a minimum A- rated international bank acceptable to the Employer.

Brief description of Contract 	______________________________________________

Name and address of Beneficiary	_______________________________________________

_________________________________ (whom the tender documents define as the Employer).

We have been informed that ________________ (hereinafter called the ‘Principal’) is submitting an offer for such Contract in response to your invitation, and that the conditions of your invitation (the 'conditions of invitation', which are set out in a document entitled Instructions to Tenderers) require his offer to be supported by a tender security.

At the request of the Principal, we (name of bank) _____________________ hereby irrevocably undertake to pay you, the Beneficiary/Employer, any sum or sums not exceeding in total the amount of _______________ (say: __________________ ) upon receipt by us of your demand in writing and your written statement (in the demand) stating that:

- the Principal has, without your agreement, withdrawn his offer after the latest time specified for its submission and before the expiry of its period of validity, or

- the Principal has refused to accept the correction of errors in his offer in accordance with such conditions of invitation, or

- you awarded the Contract to the Principal and he has failed to comply with sub-clause 1.6 of the conditions of the Contract, or

- you awarded the Contract to the Principal and he has failed to comply with sub-clause 4.2 of the conditions of the Contract.

Any demand for payment must contain your signature(s), which must be authenticated by your bankers or by a notary public. The authenticated demand and statement must be received by us at this office on or before (the date 35 days after the expiry of the validity of the Letter of Tender) ___________, when this guarantee shall expire, after which date this guarantee becomes null and void irrespective whether the original guarantee has been returned to us or not.

This guarantee is subject to the Uniform Rules for Demand Guarantees No. 758 ICC Publication 2010 (“Publication”) and for matters not covered by the Publication, the laws of (name of the applicable country) _______________ shall apply. In case of conflict, the laws of (name of the applicable country) _______________ shall prevail.

Date _____________	Signature(s) ___________________________

Annex C: Form of Performance Security

(Name of Project)

(Bank Guarantee No. ………, Dt………)

To

GUJRAT PIPAVAV PORT LTD.

Post Office Rampara-2,

Via Rajula,

District Amreli (Gujarat)

Pipavav Port - 365560

(hereinafter referred to as the “Beneficiary/Employer”)

Bank Guarantee No………., Dt………..

Expiry date:

Claim Expiry date

By this Guarantee . We, (Name of Bank), a banking company incorporated under the Companies Act, 1956 and carrying on Banking Business under The Banking Regulation Act, 1949 and having its Registered Office at ……………………… and its Corporate office at …………………… and one of Its Branch at ………………… (Hereinafter Referred To As The "Bank" Which Expression Shall Unless Repugnant To Context Or Meaning Thereof, Include Its Successors Or Assigns in business) at the request of (Contractor Name), registered office at (who is the contractor under such Contract) as Principal are irrevocably held and firmly bound to the Beneficiary in the total amount of Rs. XX,XX,XXX/- (the "Guarantee Amount". Say Rupees (in word)…………..) for the due performance of all such Principal's obligations and liabilities under the Contract.

This Guarantee shall become effective from the date of issuance of this Bank Guarantee.

Upon Default by the Principal to perform any Contractual Obligation or upon the occurrence of any of the events and circumstances listed in  -clause   of the conditions of the Contract the Guarantor shall satisfy and discharge the damages sustained by the Beneficiary due to such Default event or circumstances. However, the total liability of the Guarantor shall not exceed the Bond Amount.

The obligations and liabilities of the Guarantor shall not be discharged by any allowance of time or other indulgence whatsoever by the Beneficiary to the Principal or by any variation or suspension of the works to be executed under the Contract or by any amendments to the Contract or to the constitution of the Principal or the Beneficiary or by any other matters whether with or without the knowledge or consent of the Guarantor.

Any claim under this Guarantee must be received by the Guarantor on or before (the date six months after the expected expiry of the Defects Notification Period for the Works) Date XX/XX/XXXX (the "Expiry Date") when this Guarantee shall expire and shall be returned to the Guarantor.

The benefit of this Guarantee may be assigned subject to the provisions for assignment of the Contract and subject to the receipt by the Guarantor of evidence of full compliance with such provisions.

This Guarantee shall be governed by and construed in accordance with laws of India.

Wherefore this Guarantee has been issued by the Principal and the Guarantor on ____________(date)

Signature{s) for and on behalf of the Principal

Signature(s) for and on behalf of the Guarantor

Annex D: Form of Advance Payment Guarantee

(Name of Project)

(Bank Guarantee No. ………, Dt………)

To

GUJRAT PIPAVAV PORT LTD.

Post Office Rampara-2,

Via Rajula,

District Amreli (Gujarat)

Pipavav Port - 365560

(hereinafter referred to as the “Beneficiary/Employer”)

Bank Guarantee No………., Dt………..

Expiry date:

Claim Expiry date

We have been informed that (Contractor Name) (hereinafter called the "Principal") is your contractor under such Contract and wishes to receive an advance payment, for which the Contract requires him to obtain a guarantee.

At the request of the Principal, we (name of bank) (Address) hereby irrevocably undertake to pay you, the Beneficiary/Employer, any sum or sums not exceeding in total the amount of Rs. XX,XX,XXX/- (the "Guarantee Amount". Say Rupees (in word)…………..)upon receipt by us of your demand in writing and your written statement stating:

that the Principal has failed to repay the advance payment in accordance with the conditions of the Contract. and

the amount which the Principal has failed to repay.

This guarantee shall become effective upon the date of issuance of this Bank Guarantee. Such guaranteed amount shall be reduced by the amounts of the advance payment repaid to you, as evidenced by your notices issued under sub-clause  10 of the conditions of the Contract. Following receipt (from the Principal) of a copy of each   notice. We shall promptly notify to you by way of amendment to this Bank Guarantee.

All claims under the guarantee will be payable on receipt of a written demand made in original. The demand and statement must be received by us at this office on or before (the date 70 days after the expected expiry of the Time for Completion) Date XX/XX/XXXX (the "expiry date") when this guarantee shall expire and shall be returned to us.

We have been informed that the Beneficiary may require the Principal to extend this guarantee if the advance payment has not been repaid by the date 28 days prior to such expiry date. We undertake to pay you such guaranteed amount upon receipt by us. within such period of 28 days, of your demand in writing and your written statement that the advance payment has not been repaid and that this guarantee has not been extended.

This guarantee shall be governed by and construed in accordance with the laws of India.

Date :

Place :

Signature {s)

Annex E: Form of Dispute Adjudication Board Agreement

Name and details of Contract	_______________________________________________

Name and address of Employer	_______________________________________________

Name and address of Contractor	_______________________________________________

Name and address of Member	_______________________________________________

Whereas the Employer and the Contractor have entered into the Contract and desire jointly to appoint the Member to act as one of the three persons who are jointly called the 'DAB' [and desire the Member to act as chairman of the DAB].

The Employer, Contractor and Member jointly agree as follows:

- The conditions of this Dispute Adjudication Agreement comprise the 'General Conditions of Dispute Adjudication Agreement', which is appended to the General Conditions of the 'Conditions of Contract for Plant and Design-Build' First Edition 1999 published by the Fédération Internationale des Ingénieurs-Conseils (FIDIC), and the following provisions. In these provisions, which include amendments and additions to the General Conditions of Dispute Adjudication Agreement, words and expressions shall have the same meanings as are assigned to them in the General Conditions of Dispute Adjudication Agreement.

- In accordance with Clause 6 of the General Conditions of Dispute Adjudication Agreement, the Member shall be paid as follows:

A retainer fee of ______________ per calendar month,

plus a daily fee of _____________ per day.

- In consideration of these fees and other payments to be made by the Employer and the Contractor in accordance with Clause 6 of the General Conditions of Dispute Adjudication Agreement, the Member undertakes to serve, as described in this Dispute Adjudication Agreement, as one of the three persons who are jointly to act as the DAB.

- The Employer and the Contractor jointly and severally undertake to pay the Member, in consideration of the carrying out of these services, in accordance with Clause 6 of the General Conditions of Dispute Adjudication Agreement.

- This Dispute Adjudication Agreement shall be governed by the law of ______________.

| SIGNED by: ______________ for and on behalf of the Employer in the presence of Witness: _____________ Name: _____________ Address: _____________ Date: _____________ | SIGNED by: ______________ for and on behalf of the Contractor in the presence of Witness: _____________ Name: _____________ Address: _____________ Date: _____________ | SIGNED by: ______________ the Member in the presence of Witness: _____________ Name: _____________ Address: _____________ Date: _____________ |
| --- | --- | --- |

Form of Letter of Tender

This letter shall be printed on company letterhead.

Name of Contract:		______________________________________________

To: 				______________________________________________

We have examined the Conditions of Contract, Employer's Requirements, Schedules, the attached Appendix and Addenda Nos _____________________ or the above-named Works. We have examined, understood and checked these documents and have ascertained that they contain no errors or other defects. We accordingly offer to design, execute and complete the Works and remedy any defects therein, in conformity with this Tender which includes all these documents and the enclosed Proposal, for the lump sum of

_________________________ (INR)

We agree to abide by this Tender until _______________ and it shall remain binding upon us and may be accepted at any time before that date. We acknowledge that the Appendix to Tender forms part of this Letter of Tender.

If this offer is accepted, we will provide the specified Performance Security, commence the Works as soon as is reasonably practicable after the Commencement Date, and complete the Works in accordance with the above-named documents within the Time for Completion. We guarantee that the Works will then conform with the Schedule of Guarantees.

Unless and until a formal Agreement is prepared and executed this Letter of Tender, together with your written acceptance thereof, shall constitute a binding contract between us.

We understand that you are not bound to accept the lowest or any tender you may receive.

Signature _______________ in the capacity of ___________________________________

duly authorised to sign tenders for and on behalf of ________________________________

Address: _______________________________________________________________

Date: __________________________